## Legend & Guide
RACI MATRIX — FULFILLMENT PLATFORM UPGRADE ¦ Real-World Edition
8 tabs. Start here. Read the rules. Fill in names in Stakeholder Register before using.
RACI — What Each Letter Actually Means
R — Responsible | Does the work. Can be multiple people. If 2+ people are R, split the task — don't share it vaguely.
A — Accountable | Signs off. Gets the blame if it fails. ONE person only — no exceptions. If you want to list two, you haven't decided yet.
C — Consulted | Must give input before the task proceeds. Two-way. Limited to MAX 2 per task — if everyone is C, no one is.
I — Informed | Told after. One-way. Only people who genuinely need to know the outcome. Not a courtesy copy list.
(blank) | No role. Not involved. Resist the urge to add someone 'just in case' — it dilutes accountability.
REAL-WORLD RULES APPLIED IN THIS RACI
1. Exec Sponsor is A on 4 things only: Go/No-Go, Rollback, Vendor replacement, Budget >10% variance. Nothing else.
2. Program Manager owns the program — A on schedule, vendor tracking, cross-stream decisions, scope changes.
3. IT Lead is A on ALL technical build. SI executes under IT direction. Dual R = no real owner.
4. Workstream Lead is first-line escalation from vendors. A on workstream task delivery.
5. Finance/Procurement is A on all commercial accountability. Legal advises — Legal is never A on commercial.
6. Warehouse Ops is A on live ops continuity and disposition decisions — they live with the physical outcome.
7. Vendors are R only on their own deliverables. An internal role must always be A when vendor is R.
8. C is capped at 2 per task. I is capped at 2 per task. More than that = noise, not governance.
9. [LIVE OPS] tag = warehouse operations impact. WH must validate these tasks before execution.
10. Steering Committee is A only on strategic scope decisions. They do not own operational tasks.
TAB GUIDE
Legend & Guide | This sheet. Read first, use always.
WMS – Warehouse Core | 16 tasks. Parallel run architecture through decommission.
OMS – Order Management | 14 tasks. Order lifecycle, vendor routing, real-time ops.
Vendor Onboarding | 15 tasks. Pipeline, commercial, technical, certification.
Returns & Reverse Logistics | 13 tasks. RA workflow, disposition, credits, live ops.
Decision Register | 16 decisions. One A per decision, max 3 C's, rationale included.
Escalation Paths | 10 escalation scenarios. Vendor→WL→PM→ES. 24h SLA per level.
Stakeholder Register | Fill in names here. Role scope defined. Vendor names here.

## WMS – Warehouse Core
WMS / WAREHOUSE CORE — RACI
[LIVE OPS] tags = tasks that touch running warehouse ops. WH must validate before execution. IT leads all build; SI executes under IT direction.
ID | Phase | Task / Decision | Prog. Manager | Workstream Lead | IT / Eng Lead | SI Partner | Warehouse Ops | Finance/Proc. | Legal | Exec Sponsor | Carrier (T1) | Carrier (T2) | 3PL (T1) | 3PL (T2) | Supplier (T1) | Supplier (T2) | Tech Int. (T1) | Tech Int. (T2)
▸ Parallel Run Architecture
T001 | Initiation | Define parallel run scope, duration & cutover criteria | A | C |  |  | C |  |  | I
T002 | Initiation | Design data sync architecture between legacy & new WMS | C |  | A | R | I
T003 | Initiation | [LIVE OPS] Establish rollback trigger conditions & decision owner | A | R | C |  | R |  |  | I
T004 | Initiation | [LIVE OPS] Confirm warehouse ops continuity SLAs during parallel run | R |  |  |  | A | C |  |  | I |  | I
▸ Core WMS Build
T005 | Design | Define inventory location, bin & zone structure |  | A | C |  | R
T006 | Build | Configure pick/pack/ship rules — by vendor type & carrier |  |  | A | R | C |  |  |  | C
T007 | Build | Build inbound receipt workflows (PO-based & non-PO) |  |  | A | R | C | [7 empty] | C
T008 | Build | Configure slotting, replenishment & task interleaving logic |  | C | A | R | R
T009 | Build | Carrier label & manifest generation — per carrier type |  |  | A | R | I |  |  |  | R | R
T010 | Build | Multi-vendor order consolidation rules |  | C | A | R |  |  |  |  | C |  |  |  | C
T011 | Build | [LIVE OPS] Labour management module — must not disrupt live ops | C |  | R | R | A
▸ Testing & UAT
T012 | UAT | [LIVE OPS] Unit test WMS modules against live order volumes | I | A | R | C | R
T013 | UAT | Parallel run reconciliation — legacy vs new WMS accuracy | I | C | A |  | R
T014 | UAT | Vendor integration smoke tests — T1 vendors first |  | C | A | R |  |  |  |  | R |  | R |  | R |  | R
T015 | UAT | [LIVE OPS] Load & performance test at live warehouse throughput | I |  | A | R | C
▸ Cutover
T016 | Cutover | [LIVE OPS] Final data migration — legacy to new WMS | I | C | A | R | C
T017 | Cutover | [LIVE OPS] Go / No-Go decision gate | R | C | C |  | C |  |  | A
T018 | Cutover | [LIVE OPS] Hypercare support — week 1 | C | A | R | R | R
T019 | Post-Live | Decommission legacy WMS — after 30-day stability confirmed | R |  | A |  |  | C |  | I
R = Does the work | A = Signs off (1 per task) | C = Must be consulted | I = Kept informed

## OMS – Order Management
OMS / ORDER MANAGEMENT — RACI
IT Lead owns all build accountability. Vendor columns R = vendor does their own integration work; internal IT is always A. Max 2 C's per row.
ID | Phase | Task / Decision | Prog. Manager | Workstream Lead | IT / Eng Lead | SI Partner | Warehouse Ops | Finance/Proc. | Legal | Exec Sponsor | Carrier (T1) | Carrier (T2) | 3PL (T1) | 3PL (T2) | Supplier (T1) | Supplier (T2) | Tech Int. (T1) | Tech Int. (T2)
▸ Order Flow Design
T001 | Design | Define order states & transition rules across all vendor types | I | A | R | [5 empty] | C |  |  |  | C
T002 | Design | Design multi-vendor order splitting & routing logic |  | C | A | R |  |  |  |  | C
T003 | Design | Order priority rules — SLA tier by vendor & customer class | R | A |  |  |  | C |  |  | C
T004 | Design | Fraud & compliance rules within order flow |  | I | R |  |  | C | A
▸ Vendor Order Assignment
T005 | Build | Vendor selection engine — cost, SLA & capacity weighted |  | C | A | R |  |  |  |  | C |  |  |  | C
T006 | Build | Fallback vendor assignment rules (if T1 unavailable) |  | C | A | R | [5 empty] | R |  | R |  | R
T007 | Build | Carrier rate shopping & label selection integration |  | I | A | R |  |  |  |  | R | R |  |  |  |  | R
T008 | Build | Supplier order acknowledgement & confirmation workflow |  |  | A | R | C | [7 empty] | R | R
▸ Real-Time Operations
T009 | Build | [LIVE OPS] Order visibility dashboard — internal & vendor-facing | I | A | R |  | C
T010 | Build | [LIVE OPS] Exception management & auto-rerouting triggers |  | R | A |  | C |  |  |  | C
T011 | Build | Customer comms triggers — dispatch, delay, delivery confirmed |  | C | A | R |  |  |  |  | I
▸ Testing & Cutover
T012 | UAT | End-to-end order flow test — all vendor types & tiers |  | A | R | C | R |  |  |  | R |  | R |  | R |  | R
T013 | UAT | [LIVE OPS] Parallel OMS validation against live order data | I | C | A |  | R
T014 | Cutover | OMS cutover & legacy order migration | A | C | R | R | I
R = Does the work | A = Signs off (1 per task) | C = Must be consulted | I = Kept informed

## Vendor Onboarding
VENDOR ONBOARDING — RACI
FP owns all commercial accountability. IT owns all technical integration accountability. PM owns timeline. Vendors are R on their own deliverables only.
ID | Phase | Task / Decision | Prog. Manager | Workstream Lead | IT / Eng Lead | SI Partner | Warehouse Ops | Finance/Proc. | Legal | Exec Sponsor | Carrier (T1) | Carrier (T2) | 3PL (T1) | 3PL (T2) | Supplier (T1) | Supplier (T2) | Tech Int. (T1) | Tech Int. (T2)
▸ Pipeline Governance
T001 | Initiation | Define vendor onboarding policy & tier qualification criteria | A | I |  |  |  | R | C
T002 | Initiation | Build & maintain vendor onboarding pipeline tracker (10+ vendors) | A | R |  |  |  | I
T003 | Initiation | Approve vendor tier classification (T1/T2 per type) | A | C |  |  |  | C |  | I
▸ Commercial & Legal
T004 | Contracting | Issue & negotiate MSA per vendor type — PM owns timeline, FP owns commercial, LC owns legal | C |  |  |  |  | A | R |  | R | R | R | R | R | R | R | R
T005 | Contracting | Define & agree SLA schedules by vendor tier | A |  |  |  |  | R | I |  | C |  | C |  | C |  | C
T006 | Contracting | Negotiate data sharing & API access terms |  |  | A |  |  | I | R | [7 empty] | R | R
T007 | Contracting | Confirm insurance & liability coverage per vendor | I |  |  |  |  | A | R
▸ Technical Integration
T008 | Integration | Issue integration spec & API documentation to all vendors |  | C | A | R
T009 | Integration | Carrier EDI/API integration — T1 carriers lead, T2 follow |  | I | A | R |  |  |  |  | R | R |  |  |  |  | R
T010 | Integration | 3PL WMS connectivity & live inventory feed |  | I | A | R | [6 empty] | R | R
T011 | Integration | Supplier catalogue & PO feed integration |  | I | A | R | [8 empty] | R | R
T012 | Integration | Tech Integrator platform connection & webhook config |  | I | A | C | [10 empty] | R | R
▸ Certification
T013 | Cert | Integration certification sign-off — per vendor |  | R | A | C |  |  |  |  | R |  | R |  | R |  | R
T014 | Cert | Vendor go-live approval — T1 before T2 | A | R |  |  |  | C |  | I
T015 | Post-Live | 30-day vendor SLA performance review | A | R |  |  |  | C |  |  | I | I | I |  | I |  | I
R = Does the work | A = Signs off (1 per task) | C = Must be consulted | I = Kept informed

## Returns & Reverse Logistics
RETURNS & REVERSE LOGISTICS — RACI
WH owns disposition decisions — they live with the physical outcome. FP owns credit/chargeback accountability. IT owns all system build. Vendors R on their own process only.
ID | Phase | Task / Decision | Prog. Manager | Workstream Lead | IT / Eng Lead | SI Partner | Warehouse Ops | Finance/Proc. | Legal | Exec Sponsor | Carrier (T1) | Carrier (T2) | 3PL (T1) | 3PL (T2) | Supplier (T1) | Supplier (T2) | Tech Int. (T1) | Tech Int. (T2)
▸ Policy & Process Design
T001 | Design | Define returns policy — by vendor type & customer segment | A | R |  |  |  | C | I
T002 | Design | Design returns authorisation (RA) workflow |  | A | R | I | C
T003 | Design | Define disposition rules — restock, refurb, RTV, destroy |  | R |  |  | A | C | [6 empty] | C
T004 | Design | Set vendor credit & chargeback rules per return type |  | C |  |  |  | A | R | [5 empty] | I | I
▸ System Build
T005 | Build | Returns portal — customer-facing & internal |  | C | A | R | I
T006 | Build | [LIVE OPS] Carrier return label & collection workflow |  |  | A | R | C |  |  |  | R | R
T007 | Build | Supplier return-to-vendor (RTV) workflow — T1 first |  |  | A | R | C | [7 empty] | R | R
T008 | Build | Returns inventory reconciliation inside new WMS |  | C | A |  | R | I
T009 | Build | Vendor credit note automation & finance system integration |  | I | R | R |  | A
▸ Testing & Live Ops
T010 | UAT | End-to-end returns flow — all vendor types |  | A | R | C | R |  |  |  | R |  | R |  | R
T011 | UAT | [LIVE OPS] Parallel returns processing validation | I | C | A |  | R
T012 | Ops | [LIVE OPS] Reverse logistics SLA monitoring dashboard |  | A | R |  | C |  |  |  | I |  | I
T013 | Post-Live | Returns rate report & vendor performance scorecard | A | R |  |  |  | C |  |  | I |  |  |  | I
R = Does the work | A = Signs off (1 per task) | C = Must be consulted | I = Kept informed

## Decision Register
DECISION REGISTER — ONE ACCOUNTABLE OWNER PER DECISION. NO EXCEPTIONS.
Real-world rule: if the A owner can't make the call alone, escalate — don't add a second A. Steering Cmte = A only on strategic scope/budget decisions.
ID | Workstream | Decision | Type | WHO decides (A) | WHO inputs (C — max 3) | WHO is told (I) | Notes / Real-world constraint
D001 | WMS | Define parallel run scope & duration | Operational | Program Manager | WL, WH, IT | ES | PM owns this — ES doesn't run programs
D002 | WMS | Approve rollback to legacy WMS | Emergency | Exec Sponsor | PM, WL, IT | WH, FP | Only decision ES makes in live crisis. PM prepares; ES calls it.
D003 | WMS | WMS Go / No-Go cutover | Gate | Exec Sponsor | PM, WL, WH | SC, FP | ES signs off but PM must bring clear recommendation
D004 | WMS | Decommission legacy WMS | Operational | Program Manager | IT, FP | ES | PM owns — ES informed only after 30-day stability
D005 | OMS | Approve vendor selection engine weightings | Operational | Workstream Lead | IT, PM | FP | WL closest to the commercial logic. PM & IT input only.
D006 | OMS | Approve fallback vendor rules | Operational | Workstream Lead | IT, CT1, 3T1 | PM | WL owns. Vendor T1 consulted — they are impacted.
D007 | OMS | OMS cutover readiness sign-off | Gate | Program Manager | WL, IT | ES, WH | PM owns cutover gates. ES informed, not deciding.
D008 | Vendor | Approve vendor tier classification | Strategic | Program Manager | FP, WL | ES | PM owns programme structure. SC don't classify vendors.
D009 | Vendor | Sign MSAs — commercial terms | Financial | Finance/Proc. | LC, PM | ES | FP owns commercial. LC advises. ES only if value > threshold.
D010 | Vendor | Certify each vendor integration | Gate | IT Lead | WL, SI | PM | IT owns integration quality. WL validates business fit.
D011 | Vendor | Approve vendor go-live (per vendor) | Gate | Program Manager | WL, IT | FP, ES | PM owns the pipeline. Not a committee decision.
D012 | Returns | Approve disposition rules | Operational | Warehouse Ops | WL, FP | PM, ST1 | WH lives with physical outcome — they must own it.
D013 | Returns | Approve vendor credit & chargeback policy | Financial | Finance/Proc. | LC, WL | PM | FP owns money. LC advises on enforceability.
D014 | All | Approve budget variance > 10% | Financial | Exec Sponsor | FP, PM | SC | Real escalation trigger — ES must be A here.
D015 | All | Approve scope change requests | Strategic | Program Manager | WL, FP | ES, SC | PM owns scope unless it changes budget or timeline materially
D016 | All | Vendor replacement if SLA breach unresolved 72h+ | Operational | Program Manager | FP, LC | ES | PM escalates to ES if vendor refuses remedy — ES then calls it

## Escalation Paths
ESCALATION MATRIX — VENDOR → WORKSTREAM LEAD → PM → EXEC SPONSOR
SLA per level: 24h. Auto-escalates if unresolved. No skipping levels unless Critical severity. Owner at each step = Accountable for resolution attempt.
ID | Trigger | Sev. | Step 1 — Vendor (0–8h) | Step 2 — WL (8–24h) | Step 3 — PM (24–48h) | Step 4 — ES (48–72h) | If Unresolved at 72h
E001 | Vendor misses integration milestone | HIGH | Vendor flags delay to WL immediately | WL agrees revised date + daily check-in | PM issues formal notice; FP reviews SLA penalty clause | ES contact vendor exec; FP triggers remedy | PM proposes vendor substitution to ES
E002 | Vendor integration fails 3x in testing | HIGH | Vendor provides root cause within 4h | IT + WL triage with vendor tech lead | PM escalates to vendor account exec | SI engaged to bridge; ES approves cost | PM + ES decide: extend or substitute vendor
E003 | [LIVE OPS] Warehouse disruption from parallel run | CRIT | WH flags immediately — skip to WL | WL + IT: triage < 2h; PM alerted immediately | PM activates rollback assessment; ES briefed | ES makes go/rollback call; all hands war room | Rollback to legacy WMS; post-mortem within 24h
E004 | WMS data sync failure — legacy vs new | CRIT | IT detects; alerts WL + PM simultaneously | IT + SI: data integrity check < 1h | PM: scope impact; WH halts affected tasks | ES: halt or rollback decision | Rollback to legacy; independent data audit
E005 | Carrier misses dispatch SLA | HIGH | WH/OMS auto-flags breach; WL notified | WL contacts carrier account manager | PM issues SLA breach notice; FP applies penalty | ES: review if pattern — carrier replacement? | FP triggers contract remedy; PM finds backup carrier
E006 | Vendor onboarding blocked by contracting delay | MED | PM flags to FP + LC for priority action | WL assesses pipeline impact; reschedules if needed | PM escalates to FP lead; LC prioritises review | ES: commercial pressure on vendor if strategic | FP + LC negotiate; PM adjusts onboarding sequence
E007 | Returns volume spike impacts live warehouse | HIGH | WH escalates to WL immediately | WL + WH adjust resource allocation | PM + FP: emergency capacity decision | ES: approve additional resource/3PL overflow | 3PL T1 activated for overflow handling
E008 | Key internal resource unavailable (SPOF) | MED | PM identifies cover within team same day | WL redistributes tasks across workstream | PM + ES: approve contractor or backfill | ES approves budget for external resource | PM contracts backup resource; timeline reviewed
E009 | Data security / compliance incident | CRIT | IT + LC: immediate containment — skip levels | IT isolates; LC notifies relevant parties < 4h | PM coordinates; LC leads comms | ES: crisis decision & communications | Full incident response team; vendor liability review
E010 | Go-live date at risk — critical path slip > 2 weeks | HIGH | WL flags to PM with revised critical path | PM reviews with all WLs; produces recovery plan | PM presents options to SC: compress, descope, delay | ES + SC: date change decision | PM re-baselines; all vendors notified formally

## Stakeholder Register
STAKEHOLDER REGISTER — ROLES, NAMES & REAL-WORLD ACCOUNTABILITY SCOPE
INTERNAL ROLES — Fill in Name & Direct contact
Code | Role | Name (fill in) | What they are A for | What they are NOT A for | Escalation triggers to them | Direct contact
PM | Program Manager |  | Schedule, vendor delivery tracking, cross-stream decisions, scope changes | Individual technical build tasks, legal terms, budget (>10% variance) | Any missed milestone; vendor escalation unresolved 24h
WL | Workstream Lead |  | All tasks within their workstream, vendor issue triage (first line) | Technical architecture, commercial/legal terms, budget approval | Vendor blocks task; UAT failure; resource conflict
IT | IT / Eng Lead |  | All technical build, integration architecture, data migration, go-live infra | Commercial terms, ops process design, vendor selection | Data integrity failure; integration failure 3x; performance failure
SI | SI Partner |  | Executing build tasks assigned by IT Lead — works under IT direction | Architecture decisions, integration acceptance, budget | Technical blockers they cannot resolve internally
WH | Warehouse Ops |  | Live warehouse continuity, disposition rules, ops UAT sign-off | System build, vendor contracts, budget decisions | Any parallel run task threatening live ops
FP | Finance / Proc. |  | All commercial terms, SLA penalty enforcement, vendor credits, budget | Technical decisions, legal drafting, ops processes | SLA breach > threshold; budget variance; contract dispute
LC | Legal |  | Legal sign-off on MSAs, data sharing agreements, regulatory compliance | Commercial negotiations, technical decisions, operational tasks | Data/compliance incident; liability dispute; contract risk
ES | Exec Sponsor |  | Go/No-Go gates, rollback, vendor replacement, budget variance >10% | Day-to-day tasks, individual vendor management, build decisions | Unresolved escalation from PM > 48h; critical live ops incident
VENDOR COLUMNS — Type × Tier. Fill in actual vendor names.
Code | Type | Tier | What they are R for | What they are NOT R for | Vendor Name (fill in) | Contract owner
CT1 | Carrier | Tier 1 — Strategic | Their own API/EDI integration & label delivery | Internal routing logic, order assignment, WMS config |  | FP
CT2 | Carrier | Tier 2 — Transactional | Their own integration & spot rate provision | Anything outside their contracted lane scope |  | FP
3T1 | 3PL | Tier 1 — Strategic | WMS connectivity, inventory feed, physical fulfilment at their nodes | Internal WMS config, order routing, carrier selection |  | FP
3T2 | 3PL | Tier 2 — Transactional | Overflow fulfilment within agreed SLA scope | Permanent fulfilment flows, complex integration |  | FP
ST1 | Supplier | Tier 1 — Strategic | Catalogue feed, PO acknowledgement, drop-ship integration | Carrier selection, returns processing, internal ops |  | FP
ST2 | Supplier | Tier 2 — Transactional | PO-based delivery within agreed lead times | Drop-ship, EDI integration, returns management |  | FP
TI1 | Tech Integrator | Tier 1 — Strategic | Core platform connection, middleware, webhook config, monitoring | Architecture decisions, internal data models |  | IT
TI2 | Tech Integrator | Tier 2 — Transactional | Single-function connector delivery (label, tracking, comms) | Multi-system orchestration, data transformation |  | IT